## Cyber Security Risk Register
Cyber Security Risk Register
Risk ID | Current Status | Risk Impact | Risk Probability of Occurrence | Risk Classification | Asset/Process Affected | Risk Title | Risk Description | Owner | Risk Response Strategy | Risk Treatment Plan | Risk Creation Date | Residual Risk Impact | Residual Risk Probability of Occurrence | Residual Risk Classification | Target Treatment Date
risk-1 | Open | Major | Moderate | High | CI/CD Pipeline | Unauthorized changes committed to the production environment causing downtime or not accepted behaviour | Lack of change management in major CI/CD processes | CTO | Treat/Mitigate | Implement a change management process | 2023-02-12 | Minor | Unlikely | Low | 2023-04-01
risk-2 | Open | Major | Moderate | High | Mobile application | Lacks Periodic Security Assessments | Not performing periodic security assessment on the mobile application and CMS leaves applications and network assets vulnerable to attacks, which if exploited can affect integrity of data or lead to data compromise with financial and reputational impact. Considering the fact that applications are publicly hosted increases associated risk. | CTO | Treat/Mitigate | Define a formal vulnerability management program including regular internal, external pentests, as well as independent vulnerability assessments. | 2023-02-12 | Minor | Unlikely | Low | 2023-04-01

## ddl (hidden)
Severe | Frequent | High | Open | Treat/Mitigate | AWS Subscription | BOD
Major | Likely | Medium | Closed | Accept | Mobile application | CEO
Significant | Moderate | Low |  | Transfer | API Gateway | CFO
Minor | Unlikely |  |  |  | CMS | CTO
Negligible | Rare |  |  |  | CI/CD Pipeline | Third Party
Employees/Third party